TRAINIT

Implementation Roadmap, Acceptance Test and Operations Plan

Approval gates, quality strategy, cutover, support and future extension

| Document | TRN-IMP-001 |
| --- | --- |
| Version | 0.1 - Draft for review |
| Prepared | 14 August 2026 |
| Purpose | Turn the approved design into a controlled implementation with measurable acceptance and safe operations. |
| Execution status | Design only - no migration, import, generator, database, or deployment command has been run |

DESIGN PRINCIPLE  One public identity, one shared registration path, controlled role elevation, request-centred collaboration, auditable time, and explainable billing.

# 1. Delivery strategy

Deliver in vertical slices that prove one end-to-end business outcome at a time. The first usable slice is not 'all tables generated'; it is common registration -> application -> review -> approved role/profile. The second is client request -> assignment -> communication -> approved time. The third is billing period -> invoice -> manual payment -> receipt/audit.

# 2. Phases and approval gates

| Phase | Outputs | Exit gate |
| --- | --- | --- |
| 0. Design approval | Requirements, roles, terms, billing policy, entity names, command plan, UX direction. | Named owner approves open decisions and execution scope. |
| 1. Safe reconstruction | Legacy backup, master copy, Trainit identity, blank DB, demo isolation, public pages/theme port. | Hashes/backups recorded; public routes render; no demo leakage. |
| 2. Identity and vetting | Registration, role seeds, applications, documents, review workflow, approval promotion. | Privilege-escalation tests pass; application audit complete. |
| 3. Services and clients | Catalogue, pricing, organisation memberships, service plans, managers/billing owners. | Effective-dated prices and client scoping proven. |
| 4. Request delivery | Request intake, SLA, assignments, request workspace, shared/internal communication, notifications. | Client isolation, assignee isolation and SLA queues pass UAT. |
| 5. Time and billing | Time workflow, billing engine, invoice PDF/delivery, credits, manual payment/allocation. | Golden billing cases, idempotency and reversal tests pass. |
| 6. Reporting and hardening | Dashboards, exports, accessibility, performance, backup/restore, monitoring, security review. | Operational readiness checklist signed. |
| 7. Pilot and cutover | Selected clients/services, parallel invoice comparison, training, support and rollback window. | Pilot invoices reconcile; sponsor approves broad rollout. |

# 3. Prioritised backlog

| Priority | Capabilities |
| --- | --- |
| Must | Common registration; applications/vetting; role and record access; service/client plans; request/assignment/messages; time approval; fixed+excess billing; invoice issue; manual payments; in-app/email; audit/backups. |
| Should | SLA escalation, client hour-threshold alerts, estimate approval, availability/workload matching, credit notes, delivery retries, CSV exports, mobile-optimised time entry. |
| Could | Email reply ingestion, SMS, configurable approval chains, service bundles/pooling, client satisfaction, professional ratings, richer workload forecasting. |
| Later | Payment gateway, Associate/Apprentice payouts, native apps, external vetting integrations, PostgreSQL migration, accounting package integration. |

# 4. Acceptance scenarios

| ID | Scenario | Pass condition |
| --- | --- | --- |
| AT-01 | Public registration | A visitor registers and receives only Registered User access, even if a different role is posted. |
| AT-02 | Professional vetting | An applicant saves/submits qualifications, experience and expertise; a reviewer requests changes; approval creates the correct professional role/profile with audit history. |
| AT-03 | Client vetting | A client submits organisation/service needs; approval creates organisation, primary membership and scoped dashboard. |
| AT-04 | Organisation isolation | A client user cannot view, enumerate, download or infer another client's requests, invoices, messages or files. |
| AT-05 | Request assignment | A manager triages a request and assigns an eligible Associate/Apprentice with rate snapshot; assignee accepts/declines; history remains. |
| AT-06 | Communication visibility | Shared messages reach authorised participants; internal notes and restricted attachments never appear to clients. |
| AT-07 | Time approval | Assignee submits time; invalid/overlap entries warn; rejection returns to draft; approval locks required fields. |
| AT-08 | Included-hours split | A time entry crossing the monthly threshold is split into included/excess invoiceusage allocations without changing original hours. |
| AT-09 | Mixed-tier billing | Excess Apprentice and Associate portions use their respective immutable assignment rates; rerunning calculation produces the same draft, not duplicates. |
| AT-10 | Invoice issue | Only an approved valid draft can receive an invoice number; issue locks sources and creates immutable PDF/delivery event. |
| AT-11 | Manual payment | Billing Officer records evidence and allocates a partial payment; balance/status update; duplicate warning works. |
| AT-12 | Reversal | Authorised reversal retains original payment, reason and audit; balance restores correctly. |
| AT-13 | Notification failure | Business transaction commits, failed email retries, in-app notification remains visible and operations sees the failure. |
| AT-14 | Backup/restore | A documented restore recreates a consistent database/files snapshot and integrity/foreign-key checks pass. |
| AT-15 | Accessibility/mobile | Core registration, request, message, assignment and time workflows work by keyboard and at mobile width without clipped controls. |

# 5. Test strategy

| Layer | Coverage |
| --- | --- |
| Static checks | PHP lint for generated/current files, JavaScript syntax/lint where configured, dependency audit and secret scan. |
| Unit | State-transition guards, permissions, money/rounding, included-hours allocation, rate selection, SLA clocks and notification routing. |
| Database | Migrations up/down on disposable DB, constraints/indexes, transactions, idempotency, integrity_check and foreign_key_check. |
| Integration | Registration/application approval, request assignment, time approval, invoice issue, payment allocation/reversal and outbox delivery. |
| Security | Role posting, IDOR/record isolation, CSRF, XSS, SQL injection, file upload/download, rate limit, session/reset and audit redaction. |
| Golden billing | Fixed only, under threshold, exactly threshold, threshold split, mixed levels/rates, rejected/unbillable time, late adjustments, taxes/credits, rerun. |
| UX/accessibility | Keyboard, focus, labels/errors, contrast, screen-reader semantics, mobile layout and action feedback. |
| Operational | Email outage/retry, database busy handling, backup/restore, log correlation, invoice PDF reproducibility and scheduled billing rehearsal. |
| UAT | Representative client, Associate, Apprentice, Service Manager, Vetting Officer and Billing Officer complete realistic scenarios with no admin shortcuts. |

# 6. Definition of done

- Requirements and acceptance criteria for the slice are linked to code/tests and approved by the product owner.

- No generated module is exposed before schema, access, navigation and workflow specialisation reviews.

- All mutations validate authorisation server-side and create required history/audit events.

- Database migrations, indexes and rollback/recovery notes are included; disposable migration tests pass.

- Errors are actionable for users and safe for logs; no passwords, reset tokens, private message bodies or uploaded evidence leak into logs.

- Responsive/keyboard/accessibility review is complete for new screens.

- Billing-affecting changes include golden examples and reconciliation evidence.

- Documentation, operational runbook and support ownership are updated before release.

# 7. Cutover plan

- Approve a release candidate and freeze schema/content changes for the cutover window.

- Create verified database and file backups; record hashes, permissions and restore location.

- Run migrations and seed reference data in staging, then repeat from a clean copy to prove reproducibility.

- Deploy a narrow approved file set or controlled release package; set production secret/environment outside public content.

- Run real GET/login/role/record-scope smoke tests, create no uncontrolled financial records, and verify email queue behaviour.

- Onboard a pilot client/service and run at least one billing period in parallel with the existing manual calculation.

- Reconcile every pilot invoice line and payment; resolve variances before wider rollout.

- Keep the rollback package and legacy static site available until acceptance and a defined stability period are complete.

# 8. Operations runbook requirements

| Routine | Minimum procedure |
| --- | --- |
| Daily | Review unassigned/SLA-risk requests, failed notifications, payment exceptions, application queue and error logs. |
| Weekly | Review overdue time approvals, professional availability/capacity, storage growth, audit anomalies and backup success. |
| Monthly | Open billing periods, resolve exceptions, approve/issue invoices, reconcile payments, review receivables and close periods. |
| Backup | Database plus private files and configuration/secrets references; encrypted off-host copy; retention schedule; monitored success. |
| Restore | Named owner, exact commands/locations, recovery targets, integrity checks, file/database consistency and rehearsal schedule. |
| Access review | Active users, client memberships, professional status, privileged roles, suspended/leaver accounts and stale sessions. |
| Incident | Severity, owner, containment, evidence, client communication, recovery, postmortem and corrective-action tracking. |
| Billing correction | No edits to issued facts; use credit, adjustment or payment reversal with approval and client communication. |

# 9. Risks, decisions and owners

| Decision / risk | Required owner | Needed before |
| --- | --- | --- |
| Production rates, included hours, currencies, tax and due terms | Finance/Product | Billing implementation |
| Time approval chain and client approval rights | Operations/Product | Time workflow |
| Professional vetting evidence and retention | Vetting/Legal | Application launch |
| Client membership roles and who may see finance | Operations/Finance | Client portal UAT |
| Service SLA calendar and pause rules | Service leadership | SLA notifications |
| Email provider/from address/delivery monitoring | Technical operations | Notification UAT |
| SQLite scaling threshold and PostgreSQL trigger | Technical lead | Production readiness |
| Backup/restore RPO and RTO | Business owner/Technical ops | Go-live |
| Pilot clients and parallel-run acceptance | Product/Finance | Cutover |